## Gantt Chart
DARE-Arbo Methodology Project Management Gantt Chart
Project period: January 2026 to May 2027 ¦ Revised collaboration, validation, refinement, and dissemination timeline
ID | Workstream / Phase | Activity | Key output / milestone | Start | End | Duration (days) | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027
1 | Initiation | Protocol consolidation and governance | Approved development protocol and project controls | 2026-01-05 | 2026-01-30 | 26 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Evidence mapping | Review appraisal frameworks and methodological literature | Framework inventory and construct map | 2026-01-12 | 2026-02-27 | 47 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Evidence mapping | Map arbovirus reviews and meta-analyses | Summary tables of relevant arbovirus reviews and meta-analyses literature | 2026-01-19 | 2026-03-13 | 54 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Evidence mapping | Curate and characterize primary surveillance studies | Summary tables of primary arbovirus literature | 2026-02-02 | 2026-04-03 | 61 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Evidence mapping | Map methodological and reporting challenges requiring consideration in arbovirus surveillance studies | Summary tables of methodological and reporting features requiring appraisal | 2026-03-02 | 2026-04-30 | 60 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Framework design | Define domains, criteria, and article-outcome unit | Draft DARE-Arbo architecture | 2026-03-16 | 2026-05-15 | 61 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Framework design | Develop endpoint and measurement-pathway classifications | Endpoint-specific decision structure | 2026-04-01 | 2026-06-12 | 73 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Operationalization | Develop scoring codebook and applicability rules | Draft scoring codebook | 2026-04-20 | 2026-06-26 | 68 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Operationalization | Develop appraisal library, decision tree, and worked examples | Application guide and decision tree | 2026-05-04 | 2026-07-31 | 89 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Internal review | Internal framework review, consensus refinement, and approval for piloting | Version 1.0 framework approved for pilot testing | 2026-08-03 | 2026-08-14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Digital implementation | Build digital workspace and structured data model | Functional Streamlit workspace | 2026-07-15 | 2026-08-31 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Pilot preparation | Select diverse pilot article-outcomes | Final pilot sample and assessment inventory | 2026-08-15 | 2026-09-10 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Expression of Interest | Call circulated and applications received | Completed expression-of-interest application pool | 2026-09-22 | 2026-10-31 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Collaborator Selection | Review applications and finalize agreements | Confirmed collaborators and finalized agreements | 2026-11-02 | 2026-11-13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
15 | Orientation and Independent Appraisal | Assessor training and independent framework application | Locked independent assessment datasets | 2026-11-16 | 2026-12-18 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
16 | Data Verification and Reliability Analysis | Inter-assessor agreement assessment | Criterion-, domain-, and overall reliability results | 2027-01-04 | 2027-01-22 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
17 | Discrepancy Audit and Adjudication | Review discordant assessments and clarify decision rules | Audited discrepancies and revised operational rules | 2027-01-25 | 2027-02-12 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
18 | Framework Refinement | Revise codebook, decision tree, digital workspace, and appendices | Version-aligned final framework package | 2027-02-15 | 2027-03-19 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
19 | Manuscript Development | Draft and internally review methodology manuscript | Submission-ready manuscript and supplements | 2027-03-22 | 2027-04-30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
20 | Repository Preparation and Submission | Finalize documentation and archive materials | Archived materials and journal submission | 2027-05-03 | 2027-05-21 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Activity Register
DARE-Arbo Activity Register
ID | Workstream / Phase | Activity | Key output / milestone | Start | End | Duration (days) | Owner | Status
1 | Initiation | Protocol consolidation and governance | Approved development protocol and project controls | 2026-01-05 | 2026-01-30 | 26 | JHA, AAA, CO, EAA | Completed
2 | Evidence mapping | Review appraisal frameworks and methodological literature | Framework inventory and construct map | 2026-01-12 | 2026-02-27 | 47 | EAA, LMA, JM | Completed
3 | Evidence mapping | Map arbovirus reviews and meta-analyses | Summary tables of relevant arbovirus reviews and meta-analyses literature | 2026-01-19 | 2026-03-13 | 54 | EAA, FFA | Completed
4 | Evidence mapping | Curate and characterize primary surveillance studies | Summary tables of primary arbovirus literature | 2026-02-02 | 2026-04-03 | 61 | RNA, JBE, AOB | Completed
5 | Evidence mapping | Map methodological and reporting challenges requiring consideration in arbovirus surveillance studies | Summary tables of methodological and reporting features requiring appraisal | 2026-03-02 | 2026-04-30 | 60 | EAA, LMA, JG | Completed
6 | Framework design | Define domains, criteria, and article-outcome unit | Draft DARE-Arbo architecture | 2026-03-16 | 2026-05-15 | 61 | All team members | Completed
7 | Framework design | Develop endpoint and measurement-pathway classifications | Endpoint-specific decision structure | 2026-04-01 | 2026-06-12 | 73 | All team members | Completed
8 | Operationalization | Develop scoring codebook and applicability rules | Draft scoring codebook | 2026-04-20 | 2026-06-26 | 68 | EAA, JM, LMA (reviewed by all) | Completed
9 | Operationalization | Develop appraisal library, decision tree, and worked examples | Application guide and decision tree | 2026-05-04 | 2026-07-31 | 89 | All team members | Completed
10 | Internal review | Internal framework review, consensus refinement, and approval for piloting | Version 1.0 framework approved for pilot testing | 2026-08-03 | 2026-08-14 | 12 | EAA, AO, NS | Completed
11 | Digital implementation | Build digital workspace and structured data model | Functional Streamlit workspace | 2026-07-15 | 2026-08-31 | 48 | EAA, AO, AOB (reviewed by all) | Completed
12 | Pilot preparation | Select diverse pilot article-outcomes | Final pilot sample and assessment inventory | 2026-08-15 | 2026-09-10 | 27 | EAA, AO, AAA | Completed
13 | Expression of Interest | Call circulated and applications received | Completed expression-of-interest application pool | 2026-09-22 | 2026-10-31 | 40 | EAA, AO, AAA | In progress
14 | Collaborator Selection | Review applications and finalize agreements | Confirmed collaborators and finalized agreements | 2026-11-02 | 2026-11-13 | 12 | EAA, AO, AAA | Planned
15 | Orientation and Independent Appraisal | Assessor training and independent framework application | Locked independent assessment datasets | 2026-11-16 | 2026-12-18 | 33 | External collaborators | Planned
16 | Data Verification and Reliability Analysis | Inter-assessor agreement assessment | Criterion-, domain-, and overall reliability results | 2027-01-04 | 2027-01-22 | 19 | EAA, AO | Planned
17 | Discrepancy Audit and Adjudication | Review discordant assessments and clarify decision rules | Audited discrepancies and revised operational rules | 2027-01-25 | 2027-02-12 | 19 | All collaborators | Not started
18 | Framework Refinement | Revise codebook, decision tree, digital workspace, and appendices | Version-aligned final framework package | 2027-02-15 | 2027-03-19 | 33 | All collaborators | Not started
19 | Manuscript Development | Draft and internally review methodology manuscript | Submission-ready manuscript and supplements | 2027-03-22 | 2027-04-30 | 40 | All collaborators | Not started
20 | Repository Preparation and Submission | Finalize documentation and archive materials | Archived materials and journal submission | 2027-05-03 | 2027-05-21 | 19 | EAA | Not started

## Team_members
Name | Initial | Affiliation | Experience | Position
John Humphrey Amuasi | JHA | Global Health and Infectious Disease Research Group | Infectious Disease, Global and One Health | Group Leader (PI)
Anthony Afum-Adjei Awuah | AAAA | Global Health and Infectious Disease Research Group | Infectious Disease, arbovirus surveillance and outbreak investigation | Deputy Group Leader
Christian Obirikorang | CO | Global Health and Infectious Disease Research Group | Laboratory diagnosis, serology, molecular testing, or assay validation | Vice Dean, School of Medical Sciences
Evans Asamoah Adu | EAA | Global Health and Infectious Disease Research Group | Systematic reviews, meta-analysis, evidence appraisal, Laboratory diagnosis | PhD fellow
Leslie Mawuli Aglanu | LMA | Global Health and Infectious Disease Research Group | Evaluation of methodological and reporting frameworks, Social epidemiologist | Research fellow
Jonathan Gmanyami | JG | Global Health and Infectious Disease Research Group | Systematic reviews, meta-analysis; Global Health | Research fellow
Alexander O. Boakye | AOB | Global Health and Infectious Disease Research Group | Laboratory diagnosis, serology, molecular testing and infectious disease surveillance | Senior Research Officer
Afolabi Owoloye | AO | Mountain Top University | Artificial intelligence/Machine Learning, Biostatistics | PhD fellow
Natalia Shakela | NS | Namibia University of Science and Technology | Laboratory diagnosis | PhD fellow
Rasheda Nyamekye Aziz | RNA | Global Health and Infectious Disease Research Group | Laboratory diagnosis, serology, molecular testing | Research Assistant
Jessica Bludo Edinam | JBE | Global Health and Infectious Disease Research Group | Laboratory diagnosis, serology, molecular testing | Research Assistant
Felicia Fafa Amezugbe | FFA | Korle Bu Teaching Hospital | Epidemiology and clinical care | Medical Doctor